## task_list
S.No | Date | Task | Link to useful video | Link to useful material | Time Taken | Errors Encountered Y/N | If Yes, share the Error & Solution in error report
1 | 16th mar,2017 | Oracle ojdbc.jar setup | NA | http://www.oracle.com/technetwork/apps-tech/jdbc-112010-090769.html | 35 minutes | Y | ojdbcMaven_err
2 | 16th mar,2017 | Creation of registration form | NA | NA | 20 minutes | N | NA
3 | 16th mar,2017 | Creation of User module | NA | NA | 5 minutes | N | NA
4 | 16th mar,2017 | Adding dependencies for Hibernate configuration | NA | NA | 5 minutes | N | NA
5 | 16th mar,2017 | Establishing hibernate configurations using hibernateconfig.java | NA | NA | 10 minutes | N | NA
6 | 16th mar,2017 | Packages for dao and daoimpl | NA | NA | 20 minutes | N | NA
7 | 16th mar,2017 | UserTestCases | NA | NA | 30 minutes | N | NA
8 | 16th mar,2017 | Oracle installation | NA | http://stackoverflow.com/questions/18386346/tns-port-not-available-in-oracle-11g-express-edition-installation-issue | 120 minutes | Y | oraclesid_err
9 | 16th mar,2017 | UserController | NA | NA | 30 minutes | N | NA
10 | 16th mar,2017 | Creating controller,service and register view | NA | NA | 60 minutes | N | NA
11 | 16th mar,2017 | Testing connectivity | NA | NA | 90 minutes | N | NA
12 | 16th mar,2017 | Documentation | NA | NA | 90 minutes | N | NA
13 | 20th mar , 2017 | User module-registration | NA | NA |  | N | NA
14 | 20th mar , 2017 | User module-deletion | NA | NA |  | N | NA
15 | 20th mar , 2017 | User module-activation | NA | NA |  | N | NA
16 | 20th mar , 2017 | User module-view user | NA | NA |  | N | NA
17 | 21st mar , 2017 | Blog entry page | NA | NA |  | Y | 400badrequest_err,500internal_err
18 | 22nd Mar,2017 | Blog activate module | NA | NA |  | N | NA
19 | 22nd Mar,2017 | Blog delete module | NA | NA |  | N | NA
20 | 22nd Mar,2017 | Blog view activate module | NA | NA |  | N | NA
21 | 23nd Mar,2017 | Blog singleBlog module | NA | NA |  | N | NA
22 | 24th Mar,2017 | Blog like module | NA | NA |  | N | NA
23 | 24th Mar,2017 | BlogComment dto and ,methods | NA | NA |  | N | NA
24 | 24th Mar,2017 | Blog comment module | Pending
25 | 27th Mar,2017 | Login Page | NA | NA |  | N | NA
26 | 27th Mar,2017 | Register page styling | NA | NA |  | N | NA
27 | 27th Mar,2017 | Comment Section
28

## err_list
Error ID | Full Error | Solution | Link
ojdbcMaven_err | install ojdbc.jar in maven error | ojdbc has to be copied to E drive,then : mvn install:install-file -Dfile=ojdbc.jar -DgroupId=com.oracle -DartifactId=ojdbc6 -Dversion=11.2.0 -Dpackaging=jar | NA
orcleListener_err | oracleXEListenenr started and stopped | E:\oraclexe\app\oracle\product\11.2.0\server\network\ADMIN\listener.ora and tnsnames.ora , update host to localhost in ploace of other eg:del-stx-dl etc. | NA
dataupdation_err | data not updating if change made in oracle | every time a change is made on the database , from the back end , make sure that we commit , else , it wont be reflected in the UI | NA
400badrequest_err | bad request error for the api url | names of the function and variable clashing , change names , it works. | NA
500internal_err | internal server error | oracle for string allocates column of size 255 , we have to alter it explicitly , by writing the command : ALTER TABLE Blogs MODIFY blogContent varchar(2000); | NA